## Dashboard
Service Staffing Tracker — Sprint Planning Tracker
MVP team tracker · Update Status & % Done on Sprint Backlog · Dashboard KPIs refresh automatically
Total Steps | Done | In Progress | Blocked | % Complete | In Review | Sprint | Steps | Done
S1
S2
How to use this workbook | [5 empty] | S3
1. Update Status and % Done on the Sprint Backlog sheet (dropdowns provided). | [5 empty] | S4
2. Filter Backlog by Sprint, Owner, or Module using the table filters. | [5 empty] | S5
3. Check By Person / By Sprint sheets for progress rollups (formula-driven). | [5 empty] | S6
4. Mark Handoffs as Met when the contract criteria are satisfied. | [5 empty] | S7
5. Use Sprint Boards for manager demo talking points each sprint review. | [5 empty] | S8
6. Source of truth doc: docs/12-planning/TEAM_SPRINT_PLAN.md
Legend: update backlog Status to drive KPIs & chart
Milestones
Milestone | Sprints | Theme | Manager Demo
M1 Foundations | S1–S2 | Login, masters, requirements | Login as roles; create a requirement
M2 Pipeline | S3–S4 | Candidates + selection | Full TA pipeline on one req
M3 Close the loop | S5–S6 | Offers → onboarding → join | Candidate selected → joined
M4 Insights & harden | S7–S8 | Dashboard, import, polish | Live KPIs + Excel import

## Ownership
Module Ownership
Module / Department | Member(s) | Primary Epics | Demo Focus
Sales | Ananya | E3 Requirements | Create req → assign TA → status / SLA
Talent Acquisition (TA) | Mohit & Rohit | E4 Candidates (+ offer handoff) | Add candidate → stages → select → offer
HR | Shalu & Harsh | E6 Onboarding (+ offer accept) | Accept offer → docs / BGV → Joined
Admin | Harsh | E1 / E2 / E8 Auth, Masters, Audit, Import | Users, dropdowns, audit, CSV import
Dashboard | Saleena & Akash | E7 Dashboard | KPI cards, filters, RAG / stage views
Review | Akash & Gaurav | Cross-cutting QA | Demo checklist, bugs, acceptance
Offer ownership split: Rohit (TA) create→release · Shalu (HR) accept→onboarding
Dependency: Admin unlocks all → Sales → TA → HR → Dashboard enrichment · Review every sprint
Ceremonies
Ceremony | Cadence | Owner / Focus
Planning | Start of sprint | Module owners pick Step IDs by dependency graph
Daily | Daily | Blockers only
Review | End of sprint | Akash leads demo script; owners demo
Retro | End of sprint | Doc gaps + handoff friction

## Sprint Backlog
Sprint Backlog — Track every step (edit Status / % Done / Notes / PR Link)
Done when: UI + API (where applicable) + short test note · Link PRs to Step ID
Sprint | Step ID | Owner | Module | Track | Deliverable | Demo Line | Epic / FR | Status | % Done | Notes | PR Link
S1 | A-1 | Harsh | Admin | Admin | Login + JWT session + role-based route guards | Secure access | E1 / FR-AUTH | Not Started | 0%
S1 | A-2 | Harsh | Admin | Admin | Seed + serve Setup Lists (stages, statuses, priorities…) | Dropdowns match Excel | E2 / FR-MD | Not Started | 0%
S1 | S-1 | Ananya | Sales | Requirements | Requirements list page (table, search, basic filters) | Here's all open demand | E3-S1 / FR-REQ | Not Started | 0%
S1 | S-2 | Ananya | Sales | Requirements | Create requirement form (client, role, positions, sales owner, priority) | New req in 1 minute | E3-S1 / FR-REQ-01 | Not Started | 0%
S1 | D-S1 | Saleena | Dashboard | Dashboard | Dashboard shell + loading skeletons | Home page ready | E7 | Not Started | 0%
S1 | R-G1 | Gaurav | Review | Review | Test accounts per role (Admin/Sales/TA/HR/Lead) + login matrix | RBAC demo prep | QA | Not Started | 0%
S1 | R-A1 | Akash | Review | Review | Sprint demo script + acceptance checklist (ongoing) | Manager walkthrough ready | QA | Not Started | 0%
S2 | A-3 | Harsh | Admin | Admin | Admin Users CRUD (create/disable, assign roles) | Provision Sales/TA/HR | E1-S3 / FR-AUTH-04 | Not Started | 0%
S2 | A-4 | Harsh | Admin | Admin | Clients + Job Families CRUD | Normalized masters | E2-S2 / FR-MD-08/09 | Not Started | 0%
S2 | S-3 | Ananya | Sales | Requirements | Requirement detail page + edit | Edit without breaking Excel rules | E3 / FR-REQ | Not Started | 0%
S2 | S-4 | Ananya | Sales | Requirements | Assign TA + TA handoff date | Sales → TA handoff | E3-S2 / FR-REQ-02 | Not Started | 0%
S2 | T-M1 | Mohit | TA | Candidates | Candidates list + filter by requirement | Pipeline inventory | E4 / FR-CAN-10 | Not Started | 0%
S2 | D-S1b | Saleena | Dashboard | Dashboard | KPI card layout shell (zeros OK) | Demand cards placeholder | E7-S1 | Not Started | 0%
S2 | R-G2 | Gaurav | Review | Review | Requirements acceptance checklist vs FR-REQ | Sales module sign-off | QA | Not Started | 0%
S3 | S-5 | Ananya | Sales | Requirements | Status transitions: Active / On Hold / Cancelled / Closed | Lifecycle controls | E3-S3 / FR-REQ-08 | Not Started | 0%
S3 | S-6 | Ananya | Sales | Requirements | Derived fields: age, open/closed positions, TA handoff RAG | SLA visible without Excel formulas | E3-S4 / FR-REQ-05/06/07 | Not Started | 0%
S3 | T-M2 | Mohit | TA | Candidates | Add candidate from requirement detail (prefill client/role/owners) | Add profile in context | E4-S1 / FR-CAN-01/02/09 | Not Started | 0%
S3 | T-M3 | Mohit | TA | Candidates | Stage + feedback updates (dropdowns from masters) | Stage moves like Excel, but audited | E4-S2 / FR-CAN-03 | Not Started | 0%
S3 | T-R1 | Rohit | TA | Candidates | Candidate form validation + link integrity to Req ID | Data quality at entry | E4 / FR-CAN | Not Started | 0%
S3 | A-5 | Harsh | Admin | Admin | Wire all forms to master-data APIs | No hard-coded lists | E2-S3 | Not Started | 0%
S3 | D-S2 | Saleena | Dashboard | Dashboard | KPI cards: total reqs, positions, open/closed | Demand snapshot | E7-S1 / FR-DASH-01 | Not Started | 0%
S3 | D-A1 | Akash | Dashboard | Dashboard | Filter bar: TA owner, client, date range | Slice the book | E7-S3 / FR-DASH-07 | Not Started | 0%
S4 | S-7 | Ananya | Sales | Requirements | Role-scoped default filter (salesOwner = me) + empty/error polish | My book of business | E3 / FR-REQ-09 | Not Started | 0%
S4 | T-M4 | Mohit | TA | Candidates | Profile submitted / shortlist dates + interview round | Interview tracking | E4 / FR-CAN-04 | Not Started | 0%
S4 | T-M5 | Mohit | TA | Candidates | Candidate detail page + pipeline age / candidate RAG | Aging & risk | E4 / FR-CAN-08 | Not Started | 0%
S4 | T-R2 | Rohit | TA | Candidates | Select candidate (Selected = Yes) with business rules | Selection gate | E4-S4 / FR-CAN-05 | Not Started | 0%
S4 | A-6 | Harsh | Admin | Admin | Audit log write on mutations + Admin audit viewer | Who changed what | E8-S1/S2 / FR-AUD | Not Started | 0%
S4 | D-S3 | Saleena | Dashboard | Dashboard | KPIs: pending handoff, pipeline, selected, offers, joined | Funnel snapshot | E7 / FR-DASH-02/03 | Not Started | 0%
S4 | D-A2 | Akash | Dashboard | Dashboard | Debounced refetch + URL query sync (shareable filters) | Shareable leadership view | E7-S3 / FR-DASH-07 | Not Started | 0%
S4 | R-G3 | Gaurav | Review | Review | Candidates + duplicates + select checklist vs FR-CAN | TA module sign-off | QA | Not Started | 0%
S5 | T-M6 | Mohit | TA | Candidates | Duplicate mobile/email warning banner (with confirm) | No silent duplicates | E4-S3 / FR-CAN-06/07 | Not Started | 0%
S5 | T-R3 | Rohit | TA | Offers | Create offer from selected candidate (dates, CTC, DOJ, status) | Offer initiated | E5-S1 / FR-OFF-01 | Not Started | 0%
S5 | T-R4 | Rohit | TA | Offers | Offer list + detail; status Initiated → Released | Offer tracker | E5-S2 / FR-OFF-02 | Not Started | 0%
S5 | H-S1 | Shalu | HR | Onboarding | Onboarding list page | Join pipeline visible | E6 / FR-ONB | Not Started | 0%
S5 | H-S2 | Shalu | HR | Onboarding | Create onboarding from accepted offer + assign HR owner | HR takes ownership | E6-S1 / FR-ONB-01/02 | Not Started | 0%
S5 | A-H | Harsh | HR | HR support | Pair on onboarding RBAC / Joined position logic | HR rules enforced server-side | E6 / FR-ONB-06 | Not Started | 0%
S5 | D-S4 | Saleena | Dashboard | Dashboard | Duplicate mobiles count card | Data quality KPI | E7 / FR-DASH-04 | Not Started | 0%
S5 | D-A3 | Akash | Dashboard | Dashboard | Escalations / RED items list | What needs attention today | E7 / FR-DASH-09 | Not Started | 0%
S6 | T-R5 | Rohit | TA | Offers | Offer TAT / RAG + block invalid/conflicting offers | Offer SLA & rules | E5-S3 / FR-OFF-04/06 | Not Started | 0%
S6 | T-R6 | Rohit | TA | Offers | CTA: Accepted → Start onboarding (hand to HR) | Clean TA → HR handoff | E5 / FR-OFF-05 | Not Started | 0%
S6 | H-S3 | Shalu | HR | Onboarding | Track docs pending, BGV status, joining formalities | Pre-join checklist | E6-S2 / FR-ONB-03 | Not Started | 0%
S6 | H-S4 | Shalu | HR | Onboarding | Expected/actual DOJ + onboarding status flow | Docs → BGV → formalities → Joined | E6 / FR-ONB-04 | Not Started | 0%
S6 | A-7a | Harsh | Admin | Admin | CSV import draft + audit viewer polish | Excel migration path (draft) | E8 / FR-IMP | Not Started | 0%
S6 | D-S5 | Saleena | Dashboard | Dashboard | Candidate stage summary table | Where candidates sit | E7-S2 / FR-DASH-05 | Not Started | 0%
S6 | D-A4 | Akash | Dashboard | Dashboard | Align API aggregations with Excel KPI definitions | Parity with workbook | E7 / FR-DASH | Not Started | 0%
S6 | R-G4 | Gaurav | Review | Review | Offer → onboarding → Joined E2E checklist | End-to-end hire path | QA | Not Started | 0%
S7 | H-S5 | Shalu | HR | Onboarding | Mark Joined → closed positions update on requirement | Fill rate updates live | E6-S3 / FR-ONB-04/06 | Not Started | 0%
S7 | H-S6 | Shalu | HR | Onboarding | Onboarding TAT / RAG + cancel path if offer withdrawn | Exception handling | E6 / FR-ONB-05 | Not Started | 0%
S7 | A-7 | Harsh | Admin | Admin | CSV import validate → commit (reqs/candidates) | Excel migration path | E8-S3 / FR-IMP-01/03 | Not Started | 0%
S7 | D-S6 | Saleena | Dashboard | Dashboard | Requirement RAG summary + empty-state polish | SLA health | E7-S2 / FR-DASH-06 | Not Started | 0%
S7 | R-G5 | Gaurav | Review | Review | Dashboard KPI vs Excel sample + regression pass | Leadership confidence | QA | Not Started | 0%
S8 | ALL-1 | All owners | All | Hardening | Bug bash on own module | Quality pass | M4 | Not Started | 0%
S8 | R-G5b | Akash & Gaurav | Review | Review | Full regression + final demo script | Manager showcase ready | QA | Not Started | 0%
S8 | A-8 | Harsh | Admin | Admin | Import final + audit polish | Migration hardened | E8 | Not Started | 0%
S8 | D-S7 | Saleena & Akash | Dashboard | Dashboard | Empty/error polish on dashboard | Leadership-ready UI | E7 | Not Started | 0%
S8 | R-G6 | Gaurav | Review | Review | Bug triage board (blocker / major / minor) | Transparent quality status | QA | Not Started | 0%
Every | R-A2 | Akash | Review | Review | Smoke test critical path for merged PRs | Nothing broken before demo | QA | Not Started | 0%

## By Sprint
Sprint Boards — Focus & Manager Demo
Sprint | Theme | Manager Demo | Who Does What | Total | Done | In Progress | % Complete
S1 | Foundations | Login → create requirement | Harsh: Login, seeds, masters ¦ Ananya: Req list+create ¦ Saleena: Dashboard shell ¦ Review: role test users
S2 | Sales + Admin usable | Create user → client → req → assign TA | Ananya: Detail/edit/TA assign ¦ Harsh: Users/clients/JF ¦ Mohit: Candidates list ¦ Saleena: KPI layout
S3 | TA pipeline starts | One req with 2–3 candidates moving stages | Mohit: Add candidate/stages ¦ Rohit: Validation ¦ Ananya: Status+RAG ¦ Dashboard: KPIs+filters
S4 | Selection quality | Duplicate warning + select a candidate | Mohit: Duplicates/detail ¦ Rohit: Select ¦ Harsh: Audit ¦ Dashboard: funnel KPIs
S5 | Offers | Selected → offer released → accepted | Rohit: Offer CRUD ¦ Shalu: Onboarding create ¦ Harsh: HR RBAC help ¦ Dashboard: offers KPIs
S6 | HR join path | Accepted offer → Joined; positions closed | Shalu: Docs/BGV/DOJ ¦ Rohit: Offer RAG/CTA ¦ Harsh: Import draft ¦ Dashboard: stage/RAG
S7 | Dashboard parity | Filter dashboard; RED escalations; CSV import | Saleena/Akash: Full KPIs ¦ Shalu: Onboarding RAG ¦ Harsh: CSV import ¦ Review: KPI vs Excel
S8 | Hardening & showcase | E2E: Sales → TA → Offer → HR → Dashboard | All: Bug bash ¦ Review: Regression ¦ Harsh: Import final ¦ Dashboard: polish

## By Person
Progress by Person
Person | Primary Module | Total Steps | Done | In Progress | Blocked | % Complete
Ananya | Sales
Mohit | TA
Rohit | TA
Shalu | HR
Harsh | Admin / HR
Saleena | Dashboard
Akash | Dashboard / Review
Gaurav | Review
Note: Shared owners (e.g. Saleena & Akash) are counted on those exact Owner cell values in Sprint Backlog.

## Handoffs
Handoff Contracts
From → To | Done When (Contract) | From Owner | To Owner | Status | Notes
Admin → All | Login works; masters API returns seeded values | Harsh | All module owners | Open
Sales → TA | Requirement exists with REQ-#####, Active, TA assigned | Ananya | Mohit & Rohit | Open
TA → HR | Candidate Selected; Offer Accepted | Rohit | Shalu | Open
HR → Dashboard | Status Joined with actual DOJ; closed positions updated | Shalu | Saleena & Akash | Open
All → Review | PR linked to Step ID + short test notes | All owners | Akash & Gaurav | Open

## Manager Demo
Manager Showcase Checklist (use every sprint review ~10 min)
# | Agenda Item | Time | Where in this workbook
1 | Who owns what — ownership table | 2 min | Show Ownership sheet
2 | Steps completed — checkboxes by Step ID | 2 min | Filter Sprint Backlog by current sprint + Done
3 | Live demo — one vertical slice only | 4 min | See Sprint Boards → Manager Demo column
4 | What's next / dependencies | 1 min | Handoffs sheet + next sprint focus
5 | Risks — blockers Review found | 1 min | Filter Status = Blocked on Sprint Backlog
Per-sprint demo lines (copy into slides)
Sprint | Theme | Demo Line
S1 | Foundations | Login → create requirement
S2 | Sales + Admin usable | Create user → client → req → assign TA
S3 | TA pipeline starts | One req with 2–3 candidates moving stages
S4 | Selection quality | Duplicate warning + select a candidate
S5 | Offers | Selected → offer released → accepted
S6 | HR join path | Accepted offer → Joined; positions closed
S7 | Dashboard parity | Filter dashboard; RED escalations; CSV import
S8 | Hardening & showcase | E2E: Sales → TA → Offer → HR → Dashboard
References: docs/12-planning/TEAM_SPRINT_PLAN.md · EPICS_AND_STORIES.md · SPRINT_AND_MILESTONES.md

## Lookups (hidden)
Not Started | Ananya | Sales
In Progress | Mohit | TA
Blocked | Rohit | HR
In Review | Shalu | Admin
Done | Harsh | Dashboard
| Saleena | Review
| Akash | All
Gaurav
Saleena & Akash
Akash & Gaurav
Mohit & Rohit
All owners